## Sheet1
PRE-DESIGN FORM F7.1
PROJECT |  | Pattullo Bridge - Construction Engineering
CODE |  | 21-910
Responsible Engineer (EOR) |  | Saqib Khan
Project Manager (PM) |  | Sri Kota
Date |  | 2023-11-21
1 | Assess Competency | Yes | No | Notes
| Are qualified professionals available? | ✓
| Is IRSD required? | ✓
| Key Personnal | Expertise |  |  |  |  | Role
| Team Member 1 | [5 empty] | EOR
| Team Member 2 | [5 empty] | Lead Analyst
| Team Member 3 | [5 empty] | Design Lead
2 | Risk Assessment | Low | Medium | High | Notes
| Overall Risk Level | ✓ | ✓ | ✓
| Level of Check Required | DIRECT | INDEPDT | CAT III
| Risk Assessment Details | HAZARD & CONSEQUENCE |  |  |  | SEVERITY OF CONSEQUENCE | LIKELIHOOD OF CONSEQUENCE | LEVEL OF RISK
| Task 1 | Blah blah… |  |  |  | Catastrophic | Remote | High
| Task 2 | Blah blah… |  |  |  | Moderate | Remote | Moderate
| Task 3 | Blah blah… |  |  |  | Catastrophic | Improbable | Moderate
| RISK GUIDE | LIKELIHOOD OF CONSEQUENCE
| SEVERITY OF CONSEQUENCE | Improbable |  | Remote |  | Occasional | Probable | Frequent
| Insignificant | Minimal |  | Minimal |  | Low | Moderate | Moderate
| Minor | Minimal |  | Low |  | Moderate | Moderate | High
| Moderate | Low |  | Moderate |  | Moderate | High | High
| Critical | Moderate |  | Moderate |  | High | High | Extreme
| Catastrophic | Moderate |  | High |  | High | Extreme | Extreme
3 | Project Set-up | Yes | No | Notes
| Has project number been assigned? | ✓
| Has project folder been created? | ✓
| Has project been created in Replicon? | ✓
| Have tasks been created in Replicon? | ✓
| Have staff been assigned in Replicon? | ✓
| Have billing rates been set-up in Replicon? | ✓
| Has a co-manager been assigned? | ✓
4 | Technical Inputs | Yes | No | Notes
| Has background info/data been stored? | ✓
| Are project codes/standards outlined? | ✓
| Is design criteria document created? | ✓
| Is the analysis software selected? | ✓ |  | Outline software and/or other tools to be used
| Is the baseline concept / plan developed? | ✓
| Is an initial drawings list completed? | ✓
5 | PPMP Procedures | Yes | No | Notes
| Is the team familiar with P6.2 & P6.3? | ✓
| Are team engineers familiar with P7.2? | ✓
| Are team engineers familiar with P7.3? | ✓
| Is the team familiar with P7.4? | ✓
| Is the EOR familiar with P7.5 & C7.1? | ✓
| Is the team familiar with P7.6? | ✓
6 | Deliverables | Yes | No | Notes
| Are deliverable stages and content decided? | ✓
| Is there and intitial scehdule in place? | ✓
7 | Terms | Yes | No | Notes
| Is the client aware of monthly invoicing? | ✓
| Is the client aware of net 30? | ✓
| Is the client aware of scope inclusions and exclusions? | ✓
| Is the client aware of our PLI limit of $2M and CGL limit of $10M? | ✓
| Has it been communicated that our Limitation Of Liability for PLI is 1 x Fees? | ✓
| Has it been communicated that the copyright belongs to Spannovation unless paid in full for services rendered? | ✓
8 | Project Leaders Certifcation | SIGNATURE |  |  | DATE
a | Responsible Engineer (EOR)
b | Project Manager (PM)